## Gantt
Boards - Stories Dashboard (by months)
|  |  | May-2021 | May-2021 | May-2021 | May-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Nov-2021 | Nov-2021 | Nov-2021 | Nov-2021 | Nov-2021 | Dec-2021 | Dec-2021 | Dec-2021 | Dec-2021 | Jan-2022 | Jan-2022 | Jan-2022 | Jan-2022 | Jan-2022 | Feb-2022 | Feb-2022 | Feb-2022 | Feb-2022 | Mar-2022 | Mar-2022 | Mar-2022
| Start | End | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21
none - Define the Scope and Market Research |  |  | 10: none - Define the Scope and Market Research
Target User Research(Target User Research) | 17-May-2021 | 19-May-2021 | 17: Target User Research (17-May-21 - 19-May-21)
Research Existing Applications(Research Existing Applications) | 19-May-2021 | 19-May-2021 | 17: Research Existing Applications (19-May-21 - 19-May-21)
Explore Market Gaps(Explore Market Gaps) | 20-May-2021 | 21-May-2021 | 17: Explore Market Gaps (20-May-21 - 21-May-21)
Define Scope(Define Scope) | 22-May-2021 | 22-May-2021 | 17: Define Scope (22-May-21 - 22-May-21)
none - Design and Architecture |  |  | 10: none - Design and Architecture
Methodology and Application Architecture Design(Methodology and Application Architecture Design) | 24-May-2021 | 25-May-2021 | 24: Methodology and Application Architecture Design (24-May-21 - 25-May-21)
Define User Journey(Define User Journey) | 26-May-2021 | 26-May-2021 | 24: Define User Journey (26-May-21 - 26-May-21)
Create User Personas(Create User Personas) | 27-May-2021 | 28-May-2021 | 24: Create User Personas (27-May-21 - 28-May-21)
UX/ UI and Wireframing(UX/ UI and Wireframing) | 28-May-2021 | 01-Jun-2021 | 24: UX/ UI and Wireframing (28-May-21 - 01-Jun-21); 31: UX/ UI and Wireframing (28-May-21 - 01-Jun-21)
Early Beta Testing(Early Beta Testing) | 28-May-2021 | 01-Jun-2021 | 24: Early Beta Testing (28-May-21 - 01-Jun-21); 31: Early Beta Testing (28-May-21 - 01-Jun-21)
none - Sprint 1 - UI |  |  | 10: none - Sprint 1 - UI
Create the Main Screen UI(Create the Main Screen UI) | 03-Jun-2021 | 07-Jun-2021 | 31: Create the Main Screen UI (03-Jun-21 - 07-Jun-21); 7: Create the Main Screen UI (03-Jun-21 - 07-Jun-21)
Create the Shopping UI(Create the Shopping UI) | 08-Jun-2021 | 11-Jun-2021 | 7: Create the Shopping UI (08-Jun-21 - 11-Jun-21)
Create the Login/ Registration Screen(Create the Login/ Registration Screen) | 12-Jun-2021 | 16-Jun-2021 | 7: Create the Login/ Registration Screen (12-Jun-21 - 16-Jun-21); 14: Create the Login/ Registration Screen (12-Jun-21 - 16-Jun-21)
Create the Maps Screen(Create the Maps Screen) | 17-Jun-2021 | 19-Jun-2021 | 14: Create the Maps Screen (17-Jun-21 - 19-Jun-21)
none - Sprint 2 - Login/ Registration |  |  | 10: none - Sprint 2 - Login/ Registration
Allow the User To Login(Allow the User To Login) | 19-Jun-2021 | 22-Jun-2021 | 14: Allow the User To Login (19-Jun-21 - 22-Jun-21); 21: Allow the User To Login (19-Jun-21 - 22-Jun-21)
Allow the User to Register to the Application(Allow the User to Register to the Application) | 23-Jun-2021 | 25-Jun-2021 | 21: Allow the User to Register to the Application (23-Jun-21 - 25-Jun-21)
none - Sprint 3 - Backend 1 (Setup and Model) |  |  | 10: none - Sprint 3 - Backend 1 (Setup and Model)
Setup Firebase(Setup Firebase) | 28-Jun-2021 | 28-Jun-2021 | 28: Setup Firebase (28-Jun-21 - 28-Jun-21)
Implement the Backend to Allow for Signing In/ Out(Implement the Backend to Allow for Signing In/ Out) | 29-Jun-2021 | 05-Jul-2021 | 28: Implement the Backend to Allow for Signing In/ Out (29-Jun-21 - 05-Jul-21); 5: Implement the Backend to Allow for Signing In/ Out (29-Jun-21 - 05-Jul-21)
Create the Order Model(Create the Order Model) | 06-Jul-2021 | 09-Jul-2021 | 5: Create the Order Model (06-Jul-21 - 09-Jul-21)
Create the Barber Model(Create the Barber Model) | 12-Jul-2021 | 15-Jul-2021 | 12: Create the Barber Model (12-Jul-21 - 15-Jul-21)
none - Sprint 4 - Backend 2 (Populating and Integrating with the Frontend |  |  | 10: none - Sprint 4 - Backend 2 (Populating and Integrating with the Frontend
Allow for Inserting and Loading Categories(Allow for Inserting and Loading Categories) | 16-Jul-2021 | 19-Jul-2021 | 12: Allow for Inserting and Loading Categories (16-Jul-21 - 19-Jul-21); 19: Allow for Inserting and Loading Categories (16-Jul-21 - 19-Jul-21)
Allow for Loading Products(Allow for Loading Products) | 20-Jul-2021 | 22-Jul-2021 | 19: Allow for Loading Products (20-Jul-21 - 22-Jul-21)
Integrate with the Frontend(Integrate with the Frontend) | 23-Jul-2021 | 26-Jul-2021 | 19: Integrate with the Frontend (23-Jul-21 - 26-Jul-21); 26: Integrate with the Frontend (23-Jul-21 - 26-Jul-21)
none - Sprint 5 - Integrating Maps API |  |  | 10: none - Sprint 5 - Integrating Maps API
Setting up Google Maps API(Setting up Google Maps API) | 27-Jul-2021 | 28-Jul-2021 | 26: Setting up Google Maps API (27-Jul-21 - 28-Jul-21)
Tracking the Barber(Tracking the Barber) | 29-Jul-2021 | 05-Aug-2021 | 26: Tracking the Barber (29-Jul-21 - 05-Aug-21); 2: Tracking the Barber (29-Jul-21 - 05-Aug-21)
Presenting the Model to the Frontend(Presenting the Model to the Frontend) | 06-Aug-2021 | 10-Aug-2021 | 2: Presenting the Model to the Frontend (06-Aug-21 - 10-Aug-21); 9: Presenting the Model to the Frontend (06-Aug-21 - 10-Aug-21)
none - Testing/ Deployment |  |  | 10: none - Testing/ Deployment
Functional/ Performance/ Edge Testing(Functional/ Performance/ Edge Testing) | 11-Aug-2021 | 14-Aug-2021 | 9: Functional/ Performance/ Edge Testing (11-Aug-21 - 14-Aug-21)
Usability and User Acceptance Testing(Usability and User Acceptance Testing) | 15-Aug-2021 | 19-Aug-2021 | 9: Usability and User Acceptance Testing (15-Aug-21 - 19-Aug-21); 16: Usability and User Acceptance Testing (15-Aug-21 - 19-Aug-21)
Building/ Deployment(Building/ Deployment) | 20-Aug-2021 | 25-Aug-2021 | 16: Building/ Deployment (20-Aug-21 - 25-Aug-21); 23: Building/ Deployment (20-Aug-21 - 25-Aug-21)
none - Writeup |  |  | 10: none - Writeup
Writeup(Writeup) | 26-Aug-2021 | 14-Sep-2021 | 23: Writeup (26-Aug-21 - 14-Sep-21); 30: Writeup (26-Aug-21 - 14-Sep-21); 6: Writeup (26-Aug-21 - 14-Sep-21); 13: Writeup (26-Aug-21 - 14-Sep-21)
Bibliography(Bibliography) | 11-Sep-2021 | 14-Sep-2021 | 6: Bibliography (11-Sep-21 - 14-Sep-21); 13: Bibliography (11-Sep-21 - 14-Sep-21)