## Timeline
Board - High level dashboard (by weeks)
|  |  |  | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | May-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jun-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Jul-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Aug-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Sep-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021 | Oct-2021
| Start | End |  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
group - Background Research |  |  | group - Background Research
Target User Research(Target User Research) | 17-May-2021 | 19-May-2021 |  | 17: Target User Research (17-May-21 - 19-May-21); 18: Target User Research (17-May-21 - 19-May-21); 19: Target User Research (17-May-21 - 19-May-21)
Research Existing Applications(Research Existing Applications) | 19-May-2021 | 19-May-2021 |  | 19: Research Existing Applications (19-May-21 - 19-May-21)
Explore Market Gaps(Explore Market Gaps) | 20-May-2021 | 21-May-2021 |  | 20: Explore Market Gaps (20-May-21 - 21-May-21); 21: Explore Market Gaps (20-May-21 - 21-May-21)
Define Scope(Define Scope) | 22-May-2021 | 22-May-2021 |  | 22: Define Scope (22-May-21 - 22-May-21)
group - Design and Architecture |  |  | group - Design and Architecture
Methodology and Application Architecture Design(Methodology and Application Architecture Design) | 24-May-2021 | 25-May-2021 |  | 24: Methodology and Application Architecture Design (24-May-21 - 25-May-21); 25: Methodology and Application Architecture Design (24-May-21 - 25-May-21)
Define User Journey(Define User Journey) | 26-May-2021 | 26-May-2021 |  | 26: Define User Journey (26-May-21 - 26-May-21)
Create User Personas(Create User Personas) | 27-May-2021 | 28-May-2021 |  | 27: Create User Personas (27-May-21 - 28-May-21); 28: Create User Personas (27-May-21 - 28-May-21)
UX/ UI and Wireframing(UX/ UI and Wireframing) | 28-May-2021 | 03-Jun-2021 |  | 28: UX/ UI and Wireframing (28-May-21 - 03-Jun-21); 29: UX/ UI and Wireframing (28-May-21 - 03-Jun-21); 30: UX/ UI and Wireframing (28-May-21 - 03-Jun-21); 31: UX/ UI and Wireframing (28-May-21 - 03-Jun-21); 1: UX/ UI and Wireframing (28-May-21 - 03-Jun-21); 2: UX/ UI and Wireframing (28-May-21 - 03-Jun-21); 3: UX/ UI and Wireframing (28-May-21 - 03-Jun-21)
group - Sprint 1 - UI |  |  | group - Sprint 1 - UI
Main Screen UI(Main Screen UI) | 03-Jun-2021 | 07-Jun-2021 |  | 3: Main Screen UI (03-Jun-21 - 07-Jun-21); 4: Main Screen UI (03-Jun-21 - 07-Jun-21); 5: Main Screen UI (03-Jun-21 - 07-Jun-21); 6: Main Screen UI (03-Jun-21 - 07-Jun-21); 7: Main Screen UI (03-Jun-21 - 07-Jun-21)
Shopping UI(Shopping UI) | 08-Jun-2021 | 11-Jun-2021 |  | 8: Shopping UI (08-Jun-21 - 11-Jun-21); 9: Shopping UI (08-Jun-21 - 11-Jun-21); 10: Shopping UI (08-Jun-21 - 11-Jun-21); 11: Shopping UI (08-Jun-21 - 11-Jun-21)
Login/ Registration(Login/ Registration) | 12-Jun-2021 | 16-Jun-2021 |  | 12: Login/ Registration (12-Jun-21 - 16-Jun-21); 13: Login/ Registration (12-Jun-21 - 16-Jun-21); 14: Login/ Registration (12-Jun-21 - 16-Jun-21); 15: Login/ Registration (12-Jun-21 - 16-Jun-21); 16: Login/ Registration (12-Jun-21 - 16-Jun-21)
group - Sprint 2 - Login/ Registration |  |  | group - Sprint 2 - Login/ Registration
Login(Login) | 17-Jun-2021 | 19-Jun-2021 |  | 17: Login (17-Jun-21 - 19-Jun-21); 18: Login (17-Jun-21 - 19-Jun-21); 19: Login (17-Jun-21 - 19-Jun-21)
Registration(Registration) | 20-Jun-2021 | 22-Jun-2021 |  | 20: Registration (20-Jun-21 - 22-Jun-21); 21: Registration (20-Jun-21 - 22-Jun-21); 22: Registration (20-Jun-21 - 22-Jun-21)
group - Sprint 3 - Backend 1 (Setup and Model) |  |  | group - Sprint 3 - Backend 1 (Setup and Model)
Setup Firebase(Setup Firebase) | 23-Jun-2021 | 24-Jun-2021 |  | 23: Setup Firebase (23-Jun-21 - 24-Jun-21); 24: Setup Firebase (23-Jun-21 - 24-Jun-21)
Sign in/ Sign out(Sign in/ Sign out) | 26-Jun-2021 | 01-Jul-2021 |  | 26: Sign in/ Sign out (26-Jun-21 - 01-Jul-21); 27: Sign in/ Sign out (26-Jun-21 - 01-Jul-21); 28: Sign in/ Sign out (26-Jun-21 - 01-Jul-21); 29: Sign in/ Sign out (26-Jun-21 - 01-Jul-21); 30: Sign in/ Sign out (26-Jun-21 - 01-Jul-21); 1: Sign in/ Sign out (26-Jun-21 - 01-Jul-21)
Database Schema(Database Schema) | 02-Jul-2021 | 03-Jul-2021 |  | 2: Database Schema (02-Jul-21 - 03-Jul-21); 3: Database Schema (02-Jul-21 - 03-Jul-21)
Order Model(Order Model) | 05-Jul-2021 | 08-Jul-2021 |  | 5: Order Model (05-Jul-21 - 08-Jul-21); 6: Order Model (05-Jul-21 - 08-Jul-21); 7: Order Model (05-Jul-21 - 08-Jul-21); 8: Order Model (05-Jul-21 - 08-Jul-21)
Barber Model(Barber Model) | 09-Jul-2021 | 13-Jul-2021 |  | 9: Barber Model (09-Jul-21 - 13-Jul-21); 10: Barber Model (09-Jul-21 - 13-Jul-21); 11: Barber Model (09-Jul-21 - 13-Jul-21); 12: Barber Model (09-Jul-21 - 13-Jul-21); 13: Barber Model (09-Jul-21 - 13-Jul-21)
group - Sprint 4 - Backend 2 (Populating / Interacting with the Frontend) |  |  | group - Sprint 4 - Backend 2 (Populating / Interacting with the Frontend)
Inserting and Loading Categories(Inserting and Loading Categories) | 14-Jul-2021 | 16-Jul-2021 |  | 14: Inserting and Loading Categories (14-Jul-21 - 16-Jul-21); 15: Inserting and Loading Categories (14-Jul-21 - 16-Jul-21); 16: Inserting and Loading Categories (14-Jul-21 - 16-Jul-21)
Pulling Different Barbers from the Database(Pulling Different Barbers from the Database) | 16-Jul-2021 | 19-Jul-2021 |  | 16: Pulling Different Barbers from the Database (16-Jul-21 - 19-Jul-21); 17: Pulling Different Barbers from the Database (16-Jul-21 - 19-Jul-21); 18: Pulling Different Barbers from the Database (16-Jul-21 - 19-Jul-21); 19: Pulling Different Barbers from the Database (16-Jul-21 - 19-Jul-21)
Loading Products(Loading Products) | 19-Jul-2021 | 21-Jul-2021 |  | 19: Loading Products (19-Jul-21 - 21-Jul-21); 20: Loading Products (19-Jul-21 - 21-Jul-21); 21: Loading Products (19-Jul-21 - 21-Jul-21)
Integrating with the Frontend(Integrating with the Frontend) | 21-Jul-2021 | 04-Aug-2021 |  | 21: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 22: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 23: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 24: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 25: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 26: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 27: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 28: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 29: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 30: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 31: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 1: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 2: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 3: Integrating with the Frontend (21-Jul-21 - 04-Aug-21); 4: Integrating with the Frontend (21-Jul-21 - 04-Aug-21)
group - Sprint 5 - Barber Application |  |  | group - Sprint 5 - Barber Application
Authetication(Authetication) | 05-Aug-2021 | 09-Aug-2021 |  | 5: Authetication (05-Aug-21 - 09-Aug-21); 6: Authetication (05-Aug-21 - 09-Aug-21); 7: Authetication (05-Aug-21 - 09-Aug-21); 8: Authetication (05-Aug-21 - 09-Aug-21); 9: Authetication (05-Aug-21 - 09-Aug-21)
Uploading Products(Uploading Products) | 10-Aug-2021 | 12-Aug-2021 |  | 10: Uploading Products (10-Aug-21 - 12-Aug-21); 11: Uploading Products (10-Aug-21 - 12-Aug-21); 12: Uploading Products (10-Aug-21 - 12-Aug-21)
Dashboard(Dashboard) | 13-Aug-2021 | 20-Aug-2021 |  | 13: Dashboard (13-Aug-21 - 20-Aug-21); 14: Dashboard (13-Aug-21 - 20-Aug-21); 15: Dashboard (13-Aug-21 - 20-Aug-21); 16: Dashboard (13-Aug-21 - 20-Aug-21); 17: Dashboard (13-Aug-21 - 20-Aug-21); 18: Dashboard (13-Aug-21 - 20-Aug-21); 19: Dashboard (13-Aug-21 - 20-Aug-21); 20: Dashboard (13-Aug-21 - 20-Aug-21)
group - Writeup |  |  | group - Writeup
Finish Writeup(Finish Writeup) | 21-Aug-2021 | 12-Sep-2021 |  | 21: Finish Writeup (21-Aug-21 - 12-Sep-21); 22: Finish Writeup (21-Aug-21 - 12-Sep-21); 23: Finish Writeup (21-Aug-21 - 12-Sep-21); 24: Finish Writeup (21-Aug-21 - 12-Sep-21); 25: Finish Writeup (21-Aug-21 - 12-Sep-21); 26: Finish Writeup (21-Aug-21 - 12-Sep-21); 27: Finish Writeup (21-Aug-21 - 12-Sep-21); 28: Finish Writeup (21-Aug-21 - 12-Sep-21); 29: Finish Writeup (21-Aug-21 - 12-Sep-21); 30: Finish Writeup (21-Aug-21 - 12-Sep-21); 31: Finish Writeup (21-Aug-21 - 12-Sep-21); 1: Finish Writeup (21-Aug-21 - 12-Sep-21); 2: Finish Writeup (21-Aug-21 - 12-Sep-21); 3: Finish Writeup (21-Aug-21 - 12-Sep-21); 4: Finish Writeup (21-Aug-21 - 12-Sep-21); 5: Finish Writeup (21-Aug-21 - 12-Sep-21); 6: Finish Writeup (21-Aug-21 - 12-Sep-21); 7: Finish Writeup (21-Aug-21 - 12-Sep-21); 8: Finish Writeup (21-Aug-21 - 12-Sep-21); 9: Finish Writeup (21-Aug-21 - 12-Sep-21); 10: Finish Writeup (21-Aug-21 - 12-Sep-21); 11: Finish Writeup (21-Aug-21 - 12-Sep-21); 12: Finish Writeup (21-Aug-21 - 12-Sep-21)
Bibliography(Bibliography) | 13-Sep-2021 | 14-Sep-2021 |  | 13: Bibliography (13-Sep-21 - 14-Sep-21); 14: Bibliography (13-Sep-21 - 14-Sep-21)